## Gantt Chart
Task Name | Depends On | Assigned To | Estimated Duration | Availability (%) | Contingency (%) | Actual Duration | Start Date | End Date | 01/08 | 01/09 | 01/10 | 01/11 | 01/12 | 01/13 | 01/14 | 01/15 | 01/16 | 01/17 | 01/18 | 01/19 | 01/20 | 01/21 | 01/22 | 01/23 | 01/24 | 01/25 | 01/26 | 01/27 | 01/28 | 01/29 | 01/30 | 01/31 | 02/01 | 02/02 | 02/03 | 02/04 | 02/05 | 02/06 | 02/07 | 02/08 | 02/09 | 02/10 | 02/11 | 02/12 | 02/13 | 02/14
[9 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Requirements Gathering |  | Alice | 3 | 100 | 10 | 3 | 2024-01-08 | 2024-01-11 | M: 1; T: 1; W: 0; T: 1
Design Mockups | Requirements Gathering | Bob | 5 | 80 | 0 | 6 | 2024-01-12 | 2024-01-22 | F: 1; M: 0; T: 1; W: 1; T: 1; F: 1; M: 1
Frontend Development | Design Mockups | Alice | 10 | 100 | 20 | 12 | 2024-01-23 | 2024-02-07 | bar: T to F; M to F; M to W
Backend Development | Design Mockups | Bob | 8 | 100 | 15 | 9 | 2024-01-23 | 2024-02-02 | bar: T to F; M to F
Testing & QA | Frontend Development | Alice | 5 | 100 | 0 | 5 | 2024-02-08 | 2024-02-14 | bar: T to F; M to W

## Project Info
Project Name: | Website Redesign
Start Date: | 2024-01-08
End Date: | 2024-02-14
Total Duration (days): | 38

## Work Schedules
Employee Name | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Alice | X | X | X | X | X
Bob | X | X | X | X | X

## Holiday Schedule
Employee Name | Holiday Dates
GLOBAL | 2024-01-15
Alice | 2024-01-10
Bob | None